## Meetings
| 2014-09-16 | 2014-09-23 | 2014-09-30 | 2014-10-07 | 2014-10-14 | 2014-10-21 | 2014-10-28 | 2014-11-04 | 2014-11-11 | 2014-11-18 | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2014-12-23 | 2014-12-30 | 2015-01-07
Meetings with Sarven | - | Kick off | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update | Status update
Planed Work | Script for retrieval for ILO, approches for workflows | Lern basics (Bash, Workflow-tools) Setup time plan Learn about vocabulary | Learn Basics (More Bash, about Preprocessing and Transformation step) Script For ILO retrieval URI Desing Pattern | Scripts for TI Get a feel for Drake, Tarql | Scripts for TI | Scripts for TI | Issue fixing | Write first draft CASE | Finish TI Issue Fixing Start DB | DB scripting | DB scripting | ILO Scripting | ILO Scriptiong Write Report Poster | ILO Scriptiong Poster Write Report | Write Report create presentation | Correct report and presentation | Correct report and presentation
Hours used per week | 2014-09-23: 8.75; 2014-09-30: 8; 2014-10-07: 9; 2014-10-14: 8; 2014-10-21: 10; 2014-10-28: 16; 2014-11-04: 14; 2014-11-11: 18
Hours planned per week |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Hours differnce per week |  | -1.25 | -2 | -1 | -2 | 0 | 6 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestones | 2014-11-04: First draft available on github; 2014-11-11: Script for DB; 2014-11-25: Scripts for DB; 2014-12-16: All data from ILO, TI and DB; 2015-01-07: Abgabe CASE
Total hous planned | 2014-09-16: 180
Total hous used | 2014-09-16: 91.75
Total Hours Difference up to date | 2014-09-16: 11.75

## Blatt1
Approches for Workflows